# Development Execution Plan and Roadmap

## Avir Trekkers Web Platform

Document Version: 1.0

Date: 2026-04-12

Estimated Duration: 10-12 Weeks

## 1. Development Methodology

Approach: Agile (2-week sprints)

Total Sprints: 5-6 sprints

Sprint Duration: 2 weeks each

Daily Standups: 15-minute sync

Sprint Reviews: End of each sprint with client demo

Tools: GitHub (code), GitHub Projects (tasks), Figma (design), Vercel (deployment)

## 2. Phase Breakdown

### PHASE 0: Project Setup and Design (Week 1-2) — Sprint 0

0.1 Finalize requirements with client — PM — 2 days — Signed-off BRD and FRS

0.2 Create UI/UX wireframes (Figma) — Designer — 4 days — Wireframe screens

0.3 Design high-fidelity mockups — Designer — 4 days — Pixel-perfect designs

0.4 Client design review and approval — PM + Client — 1 day — Approved designs

0.5 Setup development environment — Dev — 1 day — GitHub repo, Next.js, Prisma, Tailwind

0.6 Setup cloud services — Dev — 1 day — NeonDB, Cloudinary, SendGrid, Vercel

0.7 Setup CI/CD pipeline — Dev — 0.5 day — GitHub Actions

0.8 Create database schema (Prisma) — Dev — 1 day — schema.prisma with all models

0.9 Seed database with test data — Dev — 0.5 day — Sample treks, bookings, reviews

### PHASE 1: Core Public Website (Week 3-4) — Sprint 1

1.1 Global layout: Navbar + Footer — Dev — 1 day

1.2 Home page: Hero Section — Dev — 1.5 days

1.3 Home page: Featured Treks — Dev — 1 day

1.4 Home page: Stats Section — Dev — 0.5 day

1.5 Home page: Social Impact Highlight — Dev — 0.5 day

1.6 Home page: Reviews Carousel — Dev — 1 day

1.7 Trek Listing Page — Dev — 1.5 days

1.8 Trek Detail Page — Dev — 1.5 days

1.9 API routes: Treks (GET) — Dev — 1 day

1.10 WhatsApp floating button — Dev — 0.5 day

### PHASE 2: Booking System and Contact (Week 5-6) — Sprint 2

2.1 Booking form: Primary registrant — Dev — 1.5 days

2.2 Booking form: Multi-participant — Dev — 2 days

2.3 Booking form: Summary and Confirm — Dev — 1 day

2.4 Booking API: Create booking — Dev — 1 day

2.5 Booking confirmation email — Dev — 1 day

2.6 Contact page — Dev — 1 day

2.7 Contact form API — Dev — 0.5 day

2.8 About Us page — Dev — 0.5 day

2.9 Social Impact page — Dev — 1 day

2.10 Review submission form — Dev — 0.5 day

### PHASE 3: Gallery and Reviews (Week 7-8) — Sprint 3

3.1 Gallery page: Grid layout — Dev — 1.5 days

3.2 Gallery: Category tabs/filters — Dev — 1 day

3.3 Gallery: Lightbox viewer — Dev — 1 day

3.4 Gallery API endpoints — Dev — 0.5 day

3.5 Reviews page — Dev — 1 day

3.6 Reviews API — Dev — 0.5 day

3.7 SEO optimization — Dev — 1 day

3.8 Performance optimization — Dev — 1 day

3.9 404 and Error pages — Dev — 0.5 day

3.10 Mobile responsiveness audit — Dev — 1 day

### PHASE 4: Admin Portal (Week 9-10) — Sprint 4

4.1 Admin auth: Login page — Dev — 1 day

4.2 Admin auth: Password reset — Dev — 0.5 day

4.3 Admin layout: Sidebar + Header — Dev — 1 day

4.4 Dashboard page — Dev — 1 day

4.5 Trek management: List — Dev — 1 day

4.6 Trek management: Create/Edit — Dev — 2 days

4.7 Trek management: Delete/Cancel — Dev — 0.5 day

4.8 Booking management: List — Dev — 1 day

4.9 Booking management: Detail — Dev — 0.5 day

4.10 Booking export: Excel — Dev — 1 day

### PHASE 5: Admin Completion and Polish (Week 11-12) — Sprint 5

5.1 Gallery management — Dev — 1.5 days

5.2 Content management: Hero — Dev — 1 day

5.3 Content management: About, Social Impact, Stats — Dev — 1 day

5.4 Review management — Dev — 1 day

5.5 Inquiry management — Dev — 0.5 day

5.6 Admin user management — Dev — 0.5 day

5.7 End-to-end testing — QA — 2 days

5.8 Bug fixes and polish — Dev — 2 days

5.9 Security audit — Dev — 0.5 day

5.10 Performance audit — Dev — 0.5 day

5.11 Client UAT — Client + PM — 2 days

5.12 Final fixes from UAT — Dev — 1 day

### PHASE 6: Deployment and Launch (Week 12+)

6.1 Domain setup and DNS configuration — Dev + Client — 0.5 day

6.2 Production environment setup — Dev — 0.5 day

6.3 SSL certificate verification — Dev — 0.5 day

6.4 Production deployment — Dev — 0.5 day

6.5 Smoke testing on production — QA — 0.5 day

6.6 Google Analytics setup — Dev — 0.5 day

6.7 Initial content upload — Client + Dev — 1 day

6.8 Admin training — Dev + PM — 0.5 day

6.9 Documentation handover — Dev — 0.5 day

6.10 Go Live

## 3. Sprint Calendar

Week 1-2: Sprint 0 — Setup and Design

Week 3-4: Sprint 1 — Core Public Website (Home, Treks)

Week 5-6: Sprint 2 — Booking System, Contact, About, Social Impact

Week 7-8: Sprint 3 — Gallery, Reviews, SEO, Performance

Week 9-10: Sprint 4 — Admin Portal Core (Auth, Treks, Bookings)

Week 11-12: Sprint 5 — Admin Completion, Testing, UAT

Week 12+: Deployment and Launch

## 4. Team Requirements

Fullstack Developer: 1-2 — Build frontend + backend + database

UI/UX Designer: 1 — Wireframes, mockups, design system

Project Manager: 1 — Client communication, sprint planning

QA Tester: 1 (part-time) — Testing in Sprint 5

## 5. Milestones

M1: Requirements Finalized — Week 1

M2: Designs Approved — Week 2

M3: Public Website Demo — Week 4

M4: Booking System Working — Week 6

M5: Public Site Complete — Week 8

M6: Admin Portal Demo — Week 10

M7: UAT Complete — Week 12

M8: Go Live — Week 12+

## 6. Phase 2 Backlog (Future Enhancements)

P2-01: Online payment gateway (Razorpay) — HIGH

P2-02: Multilingual support (Marathi, Hindi) — MEDIUM

P2-03: Blog / Articles section — MEDIUM

P2-04: Push notifications for trek updates — LOW

P2-05: Mobile app (React Native) — LOW

P2-06: Advanced analytics dashboard — MEDIUM

P2-07: Automated WhatsApp booking notifications — MEDIUM

P2-08: Waitlist feature for fully booked treks — MEDIUM

P2-09: Trek difficulty quiz/recommender — LOW

P2-10: Volunteer registration portal — LOW