## Resource Estimation
Role | Count | Rate/Hour (INR) | Weekly Hours | Sprint Duration | Total Sprints | Total Hours | Total Cost (INR) | Notes
Senior Fullstack Developer | 1 | 1500 | 40 | 2 weeks | 6 | 480 | 720000 | Primary developer - all sprints
Junior Fullstack Developer | 1 | 800 | 40 | 2 weeks | 4 | 320 | 256000 | Sprints 1-4 support
UI/UX Designer | 1 | 1200 | 40 | 2 weeks | 1 | 80 | 96000 | Sprint 0 only (design phase)
Project Manager | 1 | 1000 | 20 | 2 weeks | 6 | 240 | 240000 | Half-time across all sprints
QA Tester | 1 | 700 | 40 | 2 weeks | 1.5 | 120 | 84000 | Sprint 5 + launch support
[5 empty] | TOTAL | 1240 | 1396000

## Infrastructure Costs
Service | Plan | Monthly Cost (INR) | Annual Cost (INR) | Notes | Required From
Vercel (Hosting) | Pro | 1600 | 19200 | Next.js hosting, CI/CD, preview deploys | Month 1
NeonDB (Database) | Launch | 1900 | 22800 | Serverless PostgreSQL, auto-scaling | Month 1
Cloudinary (Images) | Plus | 7400 | 88800 | Image CDN, 25GB storage, transformations | Month 1
SendGrid (Email) | Essentials | 1500 | 18000 | 40K emails/month, templates | Month 2
Google Workspace | Business Starter | 250 | 3000 | Admin email (noreply@avirtrekkers.com) | Month 1
Domain Name (.com) | - | 1000 | 1000 | avirtrekkers.com registration | Month 1
Sentry (Error Tracking) | Team | 2100 | 25200 | Error monitoring, alerts | Month 3
Google reCAPTCHA | Free | 0 | 0 | Spam protection for forms | Month 2
Google Analytics | Free | 0 | 0 | User behavior tracking | Month 3
|  | TOTAL MONTHLY | 14750
|  | TOTAL ANNUAL | 178000

## Project Budget Summary
Category | Description | One-Time Cost (INR) | Monthly Recurring (INR) | Annual Recurring (INR) | Notes
Development | Full team development (12 weeks) | 1396000 | 0 | 0 | One-time development cost
Design | UI/UX wireframes + mockups | 96000 | 0 | 0 | Included in development
Infrastructure | Hosting + DB + CDN + Email | 0 | 14750 | 178000 | Starts from Month 1
Domain | Domain registration | 1000 | 0 | 1000 | Annual renewal
SSL | SSL Certificate | 0 | 0 | 0 | Free with Vercel
Third-party Tools | Sentry, Analytics | 0 | 2100 | 25200 | Optional but recommended
Contingency | 15% of development cost | 209400 | 0 | 0 | Buffer for scope changes
| TOTAL ONE-TIME | 1702400 |  |  | Development + contingency
| TOTAL MONTHLY RECURRING |  | 14750 |  | Infrastructure + tools
| TOTAL YEAR 1 |  |  | 1879400 | One-time + 12 months recurring
| TOTAL YEAR 2+ (Annual) |  |  | 178000 | Recurring only

## Cost Optimization Options
Option | Standard Cost | Optimized Cost | Savings | Trade-off
Vercel Free Tier | 19200 | 0 | 19200 | Limited bandwidth, no team features
NeonDB Free Tier | 22800 | 0 | 22800 | 0.5 GB storage, limited compute
Cloudinary Free Tier | 88800 | 0 | 88800 | 25 credits/month, limited transforms
SendGrid Free Tier | 18000 | 0 | 18000 | 100 emails/day limit
Sentry Free Tier | 25200 | 0 | 25200 | 5K errors/month limit
TOTAL SAVINGS |  | 0 | 174000 | Use free tiers initially, upgrade as needed
Minimum Viable Budget
Development (reduced scope) | 1000000 |  |  | Fewer features, single developer
Free Tier Infra (Year 1) | 0 |  |  | All free tiers
Domain | 1000
TOTAL MVP BUDGET | 1001000 |  |  | Bare minimum to launch