## Gantt Chart
Phase | Task ID | Task Name | Owner | Start Week | End Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | Dependencies | Status
PHASE 0: Setup & Design | S0-01 | Finalize requirements | PM | W1 | W1 | X | [13 empty] | Not Started
PHASE 0: Setup & Design | S0-02 | Create wireframes (Figma) | Designer | W1 | W2 | X | X | [12 empty] | Not Started
PHASE 0: Setup & Design | S0-03 | High-fidelity mockups | Designer | W2 | W2 |  | X | [11 empty] | S0-02 | Not Started
PHASE 0: Setup & Design | S0-04 | Client design approval | PM | W2 | W2 |  | X | [11 empty] | S0-03 | Not Started
PHASE 0: Setup & Design | S0-05 | Setup dev environment | Dev | W1 | W1 | X | [13 empty] | Not Started
PHASE 0: Setup & Design | S0-06 | Setup cloud services | Dev | W1 | W1 | X | [13 empty] | Not Started
PHASE 0: Setup & Design | S0-07 | Setup CI/CD pipeline | Dev | W2 | W2 |  | X | [11 empty] | S0-05 | Not Started
PHASE 0: Setup & Design | S0-08 | Create database schema | Dev | W2 | W2 |  | X | [11 empty] | S0-05 | Not Started
PHASE 0: Setup & Design | S0-09 | Seed test data | Dev | W2 | W2 |  | X | [11 empty] | S0-08 | Not Started
PHASE 1: Core Website | S1-01 | Navbar + Footer | Dev | W3 | W3 |  |  | X | [10 empty] | S0-04 | Not Started
PHASE 1: Core Website | S1-02 | Hero Section (slider) | Dev | W3 | W3 |  |  | X | [10 empty] | S1-01 | Not Started
PHASE 1: Core Website | S1-03 | Featured Treks section | Dev | W3 | W4 |  |  | X | X | [9 empty] | S1-01 | Not Started
PHASE 1: Core Website | S1-04 | Stats Section | Dev | W3 | W3 |  |  | X | [10 empty] | S1-01 | Not Started
PHASE 1: Core Website | S1-05 | Social Impact highlight | Dev | W3 | W3 |  |  | X | [10 empty] | S1-01 | Not Started
PHASE 1: Core Website | S1-06 | Reviews Carousel | Dev | W4 | W4 |  |  |  | X | [9 empty] | S1-01 | Not Started
PHASE 1: Core Website | S1-07 | Trek Listing Page | Dev | W3 | W4 |  |  | X | X | [9 empty] | S1-01 | Not Started
PHASE 1: Core Website | S1-08 | Trek Detail Page | Dev | W4 | W4 |  |  |  | X | [9 empty] | S1-07 | Not Started
PHASE 1: Core Website | S1-09 | Trek API endpoints | Dev | W3 | W4 |  |  | X | X | [9 empty] | S0-08 | Not Started
PHASE 1: Core Website | S1-10 | WhatsApp floating button | Dev | W3 | W3 |  |  | X | [10 empty] | S1-01 | Not Started
PHASE 2: Booking & Contact | S2-01 | Booking form: Registrant | Dev | W5 | W5 |  |  |  |  | X | [8 empty] | S1-08 | Not Started
PHASE 2: Booking & Contact | S2-02 | Multi-participant form | Dev | W5 | W6 |  |  |  |  | X | X | [7 empty] | S2-01 | Not Started
PHASE 2: Booking & Contact | S2-03 | Booking Summary & Confirm | Dev | W6 | W6 | [5 empty] | X | [7 empty] | S2-02 | Not Started
PHASE 2: Booking & Contact | S2-04 | Booking API endpoint | Dev | W5 | W6 |  |  |  |  | X | X | [7 empty] | S0-08 | Not Started
PHASE 2: Booking & Contact | S2-05 | Confirmation email | Dev | W6 | W6 | [5 empty] | X | [7 empty] | S2-04 | Not Started
PHASE 2: Booking & Contact | S2-06 | Contact page + form | Dev | W5 | W6 |  |  |  |  | X | X | [7 empty] | S1-01 | Not Started
PHASE 2: Booking & Contact | S2-07 | Contact API + notification | Dev | W6 | W6 | [5 empty] | X | [7 empty] | S2-06 | Not Started
PHASE 2: Booking & Contact | S2-08 | About Us page | Dev | W5 | W5 |  |  |  |  | X | [8 empty] | S1-01 | Not Started
PHASE 2: Booking & Contact | S2-09 | Social Impact page | Dev | W5 | W6 |  |  |  |  | X | X | [7 empty] | S1-01 | Not Started
PHASE 2: Booking & Contact | S2-10 | Review submission form | Dev | W6 | W6 | [5 empty] | X | [7 empty] | S1-01 | Not Started
PHASE 3: Gallery & Polish | S3-01 | Gallery grid layout | Dev | W7 | W7 | [6 empty] | X | [6 empty] | S1-01 | Not Started
PHASE 3: Gallery & Polish | S3-02 | Gallery category tabs | Dev | W7 | W8 | [6 empty] | X | X | [5 empty] | S3-01 | Not Started
PHASE 3: Gallery & Polish | S3-03 | Lightbox viewer | Dev | W8 | W8 | [7 empty] | X | [5 empty] | S3-01 | Not Started
PHASE 3: Gallery & Polish | S3-04 | Gallery API | Dev | W7 | W7 | [6 empty] | X | [6 empty] | S0-08 | Not Started
PHASE 3: Gallery & Polish | S3-05 | Reviews page | Dev | W7 | W8 | [6 empty] | X | X | [5 empty] | S2-10 | Not Started
PHASE 3: Gallery & Polish | S3-06 | Reviews API | Dev | W7 | W7 | [6 empty] | X | [6 empty] | S0-08 | Not Started
PHASE 3: Gallery & Polish | S3-07 | SEO optimization | Dev | W8 | W8 | [7 empty] | X | [5 empty] | All public pages | Not Started
PHASE 3: Gallery & Polish | S3-08 | Performance optimization | Dev | W8 | W8 | [7 empty] | X | [5 empty] | All public pages | Not Started
PHASE 3: Gallery & Polish | S3-09 | Error pages (404, 500) | Dev | W7 | W7 | [6 empty] | X | [6 empty] | S1-01 | Not Started
PHASE 3: Gallery & Polish | S3-10 | Mobile responsiveness audit | Dev | W8 | W8 | [7 empty] | X | [5 empty] | All public pages | Not Started
PHASE 4: Admin Portal | S4-01 | Admin login + JWT auth | Dev | W9 | W9 | [8 empty] | X |  |  |  |  | S0-08 | Not Started
PHASE 4: Admin Portal | S4-02 | Admin password reset | Dev | W9 | W9 | [8 empty] | X |  |  |  |  | S4-01 | Not Started
PHASE 4: Admin Portal | S4-03 | Admin sidebar + layout | Dev | W9 | W9 | [8 empty] | X |  |  |  |  | S4-01 | Not Started
PHASE 4: Admin Portal | S4-04 | Dashboard page | Dev | W9 | W10 | [8 empty] | X | X |  |  |  | S4-03 | Not Started
PHASE 4: Admin Portal | S4-05 | Trek list table | Dev | W9 | W10 | [8 empty] | X | X |  |  |  | S4-03 | Not Started
PHASE 4: Admin Portal | S4-06 | Trek create/edit form | Dev | W9 | W10 | [8 empty] | X | X |  |  |  | S4-03 | Not Started
PHASE 4: Admin Portal | S4-07 | Trek delete/cancel | Dev | W10 | W10 | [9 empty] | X |  |  |  | S4-06 | Not Started
PHASE 4: Admin Portal | S4-08 | Booking list (filterable) | Dev | W10 | W10 | [9 empty] | X |  |  |  | S4-03 | Not Started
PHASE 4: Admin Portal | S4-09 | Booking detail view | Dev | W10 | W10 | [9 empty] | X |  |  |  | S4-08 | Not Started
PHASE 4: Admin Portal | S4-10 | Booking Excel export | Dev | W10 | W10 | [9 empty] | X |  |  |  | S4-08 | Not Started
PHASE 5: Admin Complete & QA | S5-01 | Gallery management (admin) | Dev | W11 | W11 | [10 empty] | X |  |  | S4-03 | Not Started
PHASE 5: Admin Complete & QA | S5-02 | Hero section editor | Dev | W11 | W11 | [10 empty] | X |  |  | S4-03 | Not Started
PHASE 5: Admin Complete & QA | S5-03 | Content editors (About etc) | Dev | W11 | W11 | [10 empty] | X |  |  | S4-03 | Not Started
PHASE 5: Admin Complete & QA | S5-04 | Review moderation | Dev | W11 | W11 | [10 empty] | X |  |  | S4-03 | Not Started
PHASE 5: Admin Complete & QA | S5-05 | Inquiry management | Dev | W11 | W11 | [10 empty] | X |  |  | S4-03 | Not Started
PHASE 5: Admin Complete & QA | S5-06 | Admin user management | Dev | W11 | W11 | [10 empty] | X |  |  | S4-01 | Not Started
PHASE 5: Admin Complete & QA | S5-07 | End-to-end testing | QA | W11 | W12 | [10 empty] | X | X |  | All features | Not Started
PHASE 5: Admin Complete & QA | S5-08 | Bug fixes & polish | Dev | W11 | W12 | [10 empty] | X | X |  | S5-07 | Not Started
PHASE 5: Admin Complete & QA | S5-09 | Security audit | Dev | W12 | W12 | [11 empty] | X |  | All features | Not Started
PHASE 5: Admin Complete & QA | S5-10 | Performance audit | Dev | W12 | W12 | [11 empty] | X |  | All features | Not Started
PHASE 5: Admin Complete & QA | S5-11 | Client UAT | Client | W12 | W12 | [11 empty] | X |  | All features | Not Started
PHASE 5: Admin Complete & QA | S5-12 | UAT fixes | Dev | W12 | W13 | [11 empty] | X | X | S5-11 | Not Started
PHASE 6: Launch | S6-01 | Domain + DNS setup | Dev | W13 | W13 | [12 empty] | X | S5-12 | Not Started
PHASE 6: Launch | S6-02 | Production deployment | Dev | W13 | W13 | [12 empty] | X | S6-01 | Not Started
PHASE 6: Launch | S6-03 | Smoke testing | QA | W13 | W13 | [12 empty] | X | S6-02 | Not Started
PHASE 6: Launch | S6-04 | Content upload | Client | W13 | W13 | [12 empty] | X | S6-02 | Not Started
PHASE 6: Launch | S6-05 | Admin training | PM | W13 | W13 | [12 empty] | X | S6-02 | Not Started
PHASE 6: Launch | S6-06 | GO LIVE | All | W13 | W13 | [12 empty] | X | S6-03 | Not Started

## Milestones
Milestone | Target Week | Target Date | Status | Deliverable | Sign-off Required
M1: Requirements Finalized | Week 1 |  | Not Started | Signed BRD & FRS | Client + PM
M2: Designs Approved | Week 2 |  | Not Started | Approved Figma mockups | Client
M3: Public Website Demo | Week 4 |  | Not Started | Home page + Trek pages live on preview | Client
M4: Booking System Working | Week 6 |  | Not Started | End-to-end booking flow functional | Client + PM
M5: Public Site Complete | Week 8 |  | Not Started | All public pages live, SEO optimized | Client + PM
M6: Admin Portal Demo | Week 10 |  | Not Started | Admin CRUD for treks + bookings + export | Client
M7: UAT Complete | Week 12 |  | Not Started | All bugs fixed, client approved | Client + PM
M8: GO LIVE | Week 13 |  | Not Started | Production deployment, domain live | All Stakeholders

## Weekly Progress
Week | Sprint | Focus | Planned Tasks | Completed Tasks | Blockers | Notes | Velocity
Week 1 | Sprint 0 | Requirements + Setup | 4 | 0
Week 2 | Sprint 0 | Design + Schema | 5 | 0
Week 3 | Sprint 1 | Home Page + Treks | 7 | 0
Week 4 | Sprint 1 | Trek Detail + Polish | 3 | 0
Week 5 | Sprint 2 | Booking + Contact | 6 | 0
Week 6 | Sprint 2 | Multi-participant + Email | 4 | 0
Week 7 | Sprint 3 | Gallery + Reviews | 6 | 0
Week 8 | Sprint 3 | SEO + Performance | 4 | 0
Week 9 | Sprint 4 | Admin Auth + Treks | 6 | 0
Week 10 | Sprint 4 | Admin Bookings + Export | 4 | 0
Week 11 | Sprint 5 | Admin Content + Testing | 7 | 0
Week 12 | Sprint 5 | QA + UAT + Fixes | 5 | 0
Week 13 | Launch | Deploy + Go Live | 6 | 0