## RTM - Public Website
Req ID | Requirement Name | Module | Priority | Business Rule | User Story | Sprint | Task ID | Status | Test Case | Tested | Notes
PW-001 | Dynamic Hero Banner | Home Page | HIGH | BR-05 | US-001 | Sprint 1 | S1-02 | Not Started | TC-001 | No
PW-002 | Featured Upcoming Treks | Home Page | HIGH |  | US-001 | Sprint 1 | S1-03 | Not Started | TC-002 | No
PW-003 | Quick Stats Section | Home Page | MEDIUM |  | US-001 | Sprint 1 | S1-04 | Not Started | TC-003 | No
PW-004 | Social Impact Highlight | Home Page | HIGH |  | US-030 | Sprint 1 | S1-05 | Not Started | TC-004 | No
PW-005 | Recent Reviews Carousel | Home Page | MEDIUM | BR-03 | US-041 | Sprint 1 | S1-06 | Not Started | TC-005 | No
PW-006 | WhatsApp Floating Button | Home Page | HIGH | BR-06 | US-050 | Sprint 1 | S1-10 | Not Started | TC-006 | No
PW-007 | Navigation Bar | Layout | HIGH |  |  | Sprint 1 | S1-01 | Not Started | TC-007 | No
PW-008 | Footer | Layout | HIGH |  |  | Sprint 1 | S1-01 | Not Started | TC-008 | No
PW-010 | Trek Listing Page | Treks | HIGH |  | US-002 | Sprint 1 | S1-07 | Not Started | TC-010 | No
PW-011 | Trek Filters | Treks | MEDIUM |  | US-003 | Sprint 1 | S1-07 | Not Started | TC-011 | No
PW-012 | Trek Search | Treks | MEDIUM |  | US-003 | Sprint 1 | S1-07 | Not Started | TC-012 | No
PW-013 | Trek Detail Page | Treks | HIGH |  | US-004 | Sprint 1 | S1-08 | Not Started | TC-013 | No
PW-014 | Trek Status Badge | Treks | HIGH | BR-07 | US-005 | Sprint 1 | S1-08 | Not Started | TC-014 | No
PW-020 | Booking Form | Booking | HIGH | BR-01 | US-010 | Sprint 2 | S2-01 | Not Started | TC-020 | No
PW-021 | Primary Registrant Info | Booking | HIGH | BR-01 | US-010 | Sprint 2 | S2-01 | Not Started | TC-021 | No
PW-022 | Multi-Participant Enrollment | Booking | HIGH | BR-01 | US-011 | Sprint 2 | S2-02 | Not Started | TC-022 | No | Critical Feature
PW-023 | Participant Counter | Booking | HIGH | BR-02 | US-011 | Sprint 2 | S2-02 | Not Started | TC-023 | No
PW-024 | Remove Participant | Booking | HIGH |  | US-012 | Sprint 2 | S2-02 | Not Started | TC-024 | No
PW-025 | Booking Summary | Booking | HIGH |  | US-013 | Sprint 2 | S2-03 | Not Started | TC-025 | No
PW-026 | Booking Confirmation | Booking | HIGH |  | US-014 | Sprint 2 | S2-04 | Not Started | TC-026 | No
PW-027 | Booking Validation | Booking | HIGH | BR-02 | US-010 | Sprint 2 | S2-01 | Not Started | TC-027 | No
PW-029 | Duplicate Booking Check | Booking | MEDIUM |  | US-015 | Sprint 2 | S2-04 | Not Started | TC-029 | No
PW-030 | Gallery Landing Page | Gallery | HIGH | BR-04 | US-020 | Sprint 3 | S3-01 | Not Started | TC-030 | No
PW-031 | Gallery Categories | Gallery | HIGH | BR-04 | US-021 | Sprint 3 | S3-02 | Not Started | TC-031 | No
PW-032 | Image Grid | Gallery | HIGH |  | US-020 | Sprint 3 | S3-01 | Not Started | TC-032 | No
PW-033 | Lightbox View | Gallery | HIGH |  | US-022 | Sprint 3 | S3-03 | Not Started | TC-033 | No
PW-035 | Lazy Loading | Gallery | HIGH |  |  | Sprint 3 | S3-01 | Not Started | TC-035 | No
PW-040 | Social Impact Landing | Social Impact | HIGH |  | US-030 | Sprint 2 | S2-09 | Not Started | TC-040 | No
PW-041 | Initiative Cards | Social Impact | HIGH |  | US-031 | Sprint 2 | S2-09 | Not Started | TC-041 | No
PW-043 | Impact Numbers | Social Impact | HIGH |  | US-031 | Sprint 2 | S2-09 | Not Started | TC-043 | No
PW-050 | About Page | About Us | HIGH |  |  | Sprint 2 | S2-08 | Not Started | TC-050 | No
PW-060 | Reviews Display | Reviews | HIGH | BR-03 | US-041 | Sprint 3 | S3-05 | Not Started | TC-060 | No
PW-061 | Submit Review | Reviews | HIGH | BR-03 | US-040 | Sprint 2 | S2-10 | Not Started | TC-061 | No
PW-070 | Contact Page | Contact | HIGH | BR-06 | US-051 | Sprint 2 | S2-06 | Not Started | TC-070 | No
PW-071 | Contact Form | Contact | HIGH | BR-06 | US-051 | Sprint 2 | S2-06 | Not Started | TC-071 | No
PW-072 | WhatsApp Integration | Contact | HIGH | BR-06 | US-050 | Sprint 2 | S2-06 | Not Started | TC-072 | No
PW-076 | CAPTCHA | Contact | HIGH |  |  | Sprint 2 | S2-06 | Not Started | TC-076 | No

## RTM - Admin Portal
Req ID | Requirement Name | Module | Priority | Business Rule | User Story | Sprint | Task ID | Status | Test Case | Tested | Notes
AP-001 | Admin Login | Auth | HIGH |  | US-060 | Sprint 4 | S4-01 | Not Started | TC-101 | No
AP-002 | Session Management | Auth | HIGH |  | US-060 | Sprint 4 | S4-01 | Not Started | TC-102 | No
AP-003 | Password Reset | Auth | HIGH |  | US-061 | Sprint 4 | S4-02 | Not Started | TC-103 | No
AP-004 | Role-Based Access | Auth | MEDIUM |  | US-060 | Sprint 4 | S4-01 | Not Started | TC-104 | No
AP-010 | Dashboard Overview | Dashboard | HIGH |  |  | Sprint 4 | S4-04 | Not Started | TC-110 | No
AP-020 | Create Trek | Trek Mgmt | HIGH | BR-07 | US-070 | Sprint 4 | S4-06 | Not Started | TC-120 | No
AP-021 | Edit Trek | Trek Mgmt | HIGH |  | US-071 | Sprint 4 | S4-06 | Not Started | TC-121 | No
AP-022 | Delete Trek | Trek Mgmt | HIGH |  | US-074 | Sprint 4 | S4-07 | Not Started | TC-122 | No
AP-023 | Trek Listing Table | Trek Mgmt | HIGH |  | US-072 | Sprint 4 | S4-05 | Not Started | TC-123 | No
AP-024 | Duplicate Trek | Trek Mgmt | MEDIUM |  | US-073 | Sprint 4 | S4-06 | Not Started | TC-124 | No
AP-025 | Trek Status Toggle | Trek Mgmt | HIGH | BR-07 | US-074 | Sprint 4 | S4-07 | Not Started | TC-125 | No
AP-030 | Bookings List | Booking Mgmt | HIGH |  | US-080 | Sprint 4 | S4-08 | Not Started | TC-130 | No
AP-031 | Booking Detail View | Booking Mgmt | HIGH |  | US-081 | Sprint 4 | S4-09 | Not Started | TC-131 | No
AP-032 | Export Bookings (Excel) | Booking Mgmt | HIGH |  | US-082 | Sprint 4 | S4-10 | Not Started | TC-132 | No | Critical for client
AP-033 | Booking Status Update | Booking Mgmt | MEDIUM |  | US-083 | Sprint 4 | S4-09 | Not Started | TC-133 | No
AP-040 | Upload Images | Gallery Mgmt | HIGH | BR-04 | US-090 | Sprint 5 | S5-01 | Not Started | TC-140 | No
AP-041 | Manage Categories | Gallery Mgmt | HIGH | BR-04 | US-091 | Sprint 5 | S5-01 | Not Started | TC-141 | No
AP-044 | Delete Images | Gallery Mgmt | HIGH |  | US-092 | Sprint 5 | S5-01 | Not Started | TC-144 | No
AP-050 | Hero Section Editor | Content Mgmt | HIGH | BR-05 | US-100 | Sprint 5 | S5-02 | Not Started | TC-150 | No
AP-051 | About Us Editor | Content Mgmt | HIGH |  | US-101 | Sprint 5 | S5-03 | Not Started | TC-151 | No
AP-052 | Social Impact Editor | Content Mgmt | HIGH |  | US-102 | Sprint 5 | S5-03 | Not Started | TC-152 | No
AP-053 | Stats Editor | Content Mgmt | MEDIUM |  | US-103 | Sprint 5 | S5-03 | Not Started | TC-153 | No
AP-060 | Review Queue | Review Mgmt | HIGH | BR-03 | US-110 | Sprint 5 | S5-04 | Not Started | TC-160 | No
AP-061 | Approve/Reject Reviews | Review Mgmt | HIGH | BR-03 | US-110 | Sprint 5 | S5-04 | Not Started | TC-161 | No
AP-062 | Feature Review | Review Mgmt | MEDIUM |  | US-111 | Sprint 5 | S5-04 | Not Started | TC-162 | No
AP-070 | Inquiries List | Inquiry Mgmt | HIGH |  | US-112 | Sprint 5 | S5-05 | Not Started | TC-170 | No
AP-071 | Inquiry Detail | Inquiry Mgmt | HIGH |  | US-112 | Sprint 5 | S5-05 | Not Started | TC-171 | No
AP-080 | Admin User List | Admin Users | HIGH |  |  | Sprint 5 | S5-06 | Not Started | TC-180 | No
AP-081 | Add Admin User | Admin Users | HIGH |  |  | Sprint 5 | S5-06 | Not Started | TC-181 | No

## Summary
Category | Total Requirements | HIGH Priority | MEDIUM Priority | LOW Priority | Mapped to User Stories | Mapped to Sprint Tasks | Completion %
Public Website - Home Page | 8 | 5 | 3 | 0 | 8 | 8 | 0%
Public Website - Treks | 5 | 3 | 2 | 0 | 5 | 5 | 0%
Public Website - Booking | 10 | 8 | 2 | 0 | 10 | 10 | 0%
Public Website - Gallery | 7 | 5 | 2 | 0 | 7 | 7 | 0%
Public Website - Social Impact | 5 | 3 | 1 | 1 | 5 | 5 | 0%
Public Website - Reviews | 4 | 3 | 1 | 0 | 4 | 4 | 0%
Public Website - Contact | 7 | 4 | 1 | 2 | 7 | 7 | 0%
Admin - Auth | 4 | 3 | 1 | 0 | 4 | 4 | 0%
Admin - Dashboard | 3 | 1 | 2 | 0 | 3 | 3 | 0%
Admin - Trek Mgmt | 6 | 4 | 1 | 1 | 6 | 6 | 0%
Admin - Booking Mgmt | 6 | 3 | 2 | 1 | 6 | 6 | 0%
Admin - Gallery Mgmt | 6 | 3 | 2 | 1 | 6 | 6 | 0%
Admin - Content Mgmt | 6 | 3 | 2 | 1 | 6 | 6 | 0%
Admin - Review Mgmt | 4 | 2 | 1 | 1 | 4 | 4 | 0%
Admin - Inquiry Mgmt | 4 | 2 | 2 | 0 | 4 | 4 | 0%
Admin - User Mgmt | 4 | 2 | 1 | 1 | 4 | 4 | 0%
TOTAL | 89 | 54 | 26 | 9 | 89 | 89 | 0%