## Sprint Backlog
Sprint | Task ID | Task Name | Epic/Module | Assigned To | Priority | Estimated Hours | Actual Hours | Status | Start Date | End Date | Notes
Sprint 0 | S0-01 | Finalize requirements with client | Setup | PM | HIGH | 16 |  | Not Started
Sprint 0 | S0-02 | Create UI/UX wireframes (Figma) | Design | Designer | HIGH | 32 |  | Not Started
Sprint 0 | S0-03 | Design high-fidelity mockups | Design | Designer | HIGH | 32 |  | Not Started
Sprint 0 | S0-04 | Client design review & approval | Design | PM + Client | HIGH | 8 |  | Not Started
Sprint 0 | S0-05 | Setup dev environment (Next.js, Prisma, Tailwind) | Setup | Dev | HIGH | 8 |  | Not Started
Sprint 0 | S0-06 | Setup cloud services (NeonDB, Cloudinary, SendGrid) | Setup | Dev | HIGH | 8 |  | Not Started
Sprint 0 | S0-07 | Setup CI/CD pipeline (GitHub Actions) | Setup | Dev | MEDIUM | 4 |  | Not Started
Sprint 0 | S0-08 | Create database schema (Prisma) | Setup | Dev | HIGH | 8 |  | Not Started
Sprint 0 | S0-09 | Seed database with test data | Setup | Dev | MEDIUM | 4 |  | Not Started
Sprint 1 | S1-01 | Global layout: Navbar + Footer | Public Site | Dev | HIGH | 8 |  | Not Started
Sprint 1 | S1-02 | Home page: Hero Section (dynamic slider) | Home Page | Dev | HIGH | 12 |  | Not Started
Sprint 1 | S1-03 | Home page: Featured Upcoming Treks | Home Page | Dev | HIGH | 8 |  | Not Started
Sprint 1 | S1-04 | Home page: Stats Section (animated counters) | Home Page | Dev | MEDIUM | 4 |  | Not Started
Sprint 1 | S1-05 | Home page: Social Impact Highlight | Home Page | Dev | HIGH | 4 |  | Not Started
Sprint 1 | S1-06 | Home page: Reviews Carousel | Home Page | Dev | MEDIUM | 8 |  | Not Started
Sprint 1 | S1-07 | Trek Listing Page (grid, pagination) | Treks | Dev | HIGH | 12 |  | Not Started
Sprint 1 | S1-08 | Trek Detail Page | Treks | Dev | HIGH | 12 |  | Not Started
Sprint 1 | S1-09 | API routes: Treks GET endpoints | Treks | Dev | HIGH | 8 |  | Not Started
Sprint 1 | S1-10 | WhatsApp floating button | Public Site | Dev | HIGH | 4 |  | Not Started
Sprint 2 | S2-01 | Booking form: Primary registrant step | Booking | Dev | HIGH | 12 |  | Not Started
Sprint 2 | S2-02 | Booking form: Multi-participant enrollment | Booking | Dev | HIGH | 16 |  | Not Started
Sprint 2 | S2-03 | Booking form: Summary & Confirm step | Booking | Dev | HIGH | 8 |  | Not Started
Sprint 2 | S2-04 | Booking API: Create booking endpoint | Booking | Dev | HIGH | 8 |  | Not Started
Sprint 2 | S2-05 | Booking confirmation email template | Booking | Dev | HIGH | 8 |  | Not Started
Sprint 2 | S2-06 | Contact page (form + all channels) | Contact | Dev | HIGH | 8 |  | Not Started
Sprint 2 | S2-07 | Contact form API + email notification | Contact | Dev | HIGH | 4 |  | Not Started
Sprint 2 | S2-08 | About Us page | About | Dev | MEDIUM | 4 |  | Not Started
Sprint 2 | S2-09 | Social Impact page | Social Impact | Dev | HIGH | 8 |  | Not Started
Sprint 2 | S2-10 | Review submission form | Reviews | Dev | MEDIUM | 4 |  | Not Started
Sprint 3 | S3-01 | Gallery page: Responsive grid layout | Gallery | Dev | HIGH | 12 |  | Not Started
Sprint 3 | S3-02 | Gallery: Category tabs/filters | Gallery | Dev | HIGH | 8 |  | Not Started
Sprint 3 | S3-03 | Gallery: Lightbox viewer | Gallery | Dev | HIGH | 8 |  | Not Started
Sprint 3 | S3-04 | Gallery API endpoints | Gallery | Dev | HIGH | 4 |  | Not Started
Sprint 3 | S3-05 | Reviews display page | Reviews | Dev | HIGH | 8 |  | Not Started
Sprint 3 | S3-06 | Reviews API (GET, POST) | Reviews | Dev | HIGH | 4 |  | Not Started
Sprint 3 | S3-07 | SEO optimization (meta, OG, sitemap) | Performance | Dev | HIGH | 8 |  | Not Started
Sprint 3 | S3-08 | Performance optimization | Performance | Dev | HIGH | 8 |  | Not Started
Sprint 3 | S3-09 | 404 & Error pages | Public Site | Dev | MEDIUM | 4 |  | Not Started
Sprint 3 | S3-10 | Mobile responsiveness audit & fixes | Public Site | Dev | HIGH | 8 |  | Not Started
Sprint 4 | S4-01 | Admin auth: Login page + JWT | Admin | Dev | HIGH | 8 |  | Not Started
Sprint 4 | S4-02 | Admin auth: Password reset flow | Admin | Dev | HIGH | 4 |  | Not Started
Sprint 4 | S4-03 | Admin layout: Sidebar + Header | Admin | Dev | HIGH | 8 |  | Not Started
Sprint 4 | S4-04 | Admin Dashboard page | Admin | Dev | HIGH | 8 |  | Not Started
Sprint 4 | S4-05 | Trek management: List (table, search, sort) | Admin Treks | Dev | HIGH | 8 |  | Not Started
Sprint 4 | S4-06 | Trek management: Create/Edit form | Admin Treks | Dev | HIGH | 16 |  | Not Started
Sprint 4 | S4-07 | Trek management: Delete/Cancel | Admin Treks | Dev | HIGH | 4 |  | Not Started
Sprint 4 | S4-08 | Booking management: List (filterable) | Admin Bookings | Dev | HIGH | 8 |  | Not Started
Sprint 4 | S4-09 | Booking management: Detail view | Admin Bookings | Dev | HIGH | 4 |  | Not Started
Sprint 4 | S4-10 | Booking export as Excel (.xlsx) | Admin Bookings | Dev | HIGH | 8 |  | Not Started
Sprint 5 | S5-01 | Admin Gallery management (upload, categorize, delete) | Admin Gallery | Dev | HIGH | 12 |  | Not Started
Sprint 5 | S5-02 | Content management: Hero section editor | Admin Content | Dev | HIGH | 8 |  | Not Started
Sprint 5 | S5-03 | Content management: About, Social Impact, Stats | Admin Content | Dev | HIGH | 8 |  | Not Started
Sprint 5 | S5-04 | Review management (approve/reject/feature) | Admin Reviews | Dev | HIGH | 8 |  | Not Started
Sprint 5 | S5-05 | Inquiry management (view, read/unread, reply) | Admin Inquiries | Dev | MEDIUM | 4 |  | Not Started
Sprint 5 | S5-06 | Admin user management (add/edit/deactivate) | Admin Users | Dev | MEDIUM | 4 |  | Not Started
Sprint 5 | S5-07 | End-to-end testing (all flows) | QA | QA | HIGH | 16 |  | Not Started
Sprint 5 | S5-08 | Bug fixes & UI polish | QA | Dev | HIGH | 16 |  | Not Started
Sprint 5 | S5-09 | Security audit (OWASP, validation, rate limiting) | QA | Dev | HIGH | 4 |  | Not Started
Sprint 5 | S5-10 | Performance audit (Lighthouse, CWV) | QA | Dev | HIGH | 4 |  | Not Started
Sprint 5 | S5-11 | Client UAT (User Acceptance Testing) | QA | Client + PM | HIGH | 16 |  | Not Started
Sprint 5 | S5-12 | Final fixes from UAT feedback | QA | Dev | HIGH | 8 |  | Not Started

## Sprint Summary
Sprint | Duration | Focus Area | Total Tasks | Completed | In Progress | Not Started | Completion %
Sprint 0 | Week 1-2 | Setup & Design | 9 | 0 | 0 | 9 | 0%
Sprint 1 | Week 3-4 | Core Public Website | 10 | 0 | 0 | 10 | 0%
Sprint 2 | Week 5-6 | Booking, Contact, About | 10 | 0 | 0 | 10 | 0%
Sprint 3 | Week 7-8 | Gallery, Reviews, SEO | 10 | 0 | 0 | 10 | 0%
Sprint 4 | Week 9-10 | Admin Portal Core | 10 | 0 | 0 | 10 | 0%
Sprint 5 | Week 11-12 | Admin Completion & QA | 12 | 0 | 0 | 12 | 0%
TOTAL | 12 Weeks | Full Project | 61 | 0 | 0 | 61 | 0%